## Slide 1: GEF Project Cycle
GEF Expanded Constituency Workshop
11 – 13 October 2011
Tashkent, Uzbekistan
Notes: <number>
GEF Expanded Constituency Workshop

## Slide 2: GEF Project Cycle
The GEF project cycle is a process involving many partners on the frontline: countries, GEF Agencies, GEF Secretariat, GEF Council, and partners.
Other important partners perform behind the scene functions:
Trustee who sets aside funds for projects, commits funds and transfer funds;
STAP who screens projects upstream and provides scientific guidance for the project or program;
Evaluation Office which evaluates completed projects and selected themes and undertakes annual performance reviews;
Convention secretariats, also provides guidance and comments on projects.

## Slide 3: GEF Institutional Framework
GEF
Secretariat
GEF Agencies
UNDP
UNEP
World Bank
ADB
AFDB
EBRD
FAO
IADB
IFAD
UNIDO
Evaluation Office
STAP
GEF Council
Countries:
Council Members/
Constituencies;
Consultations with CSOs
Conventions
Countries:
Convention FPs
GEF Assembly
Countries:
Political FPs
Projects
Countries:
Operational FPs, Convention FPs, other gov’t agencies, civil society
Strategic Guidance
Operations
Action
Work Program
Project review
Project Development
Project idea,
endorsement,
Project implementation

## Slide 4: From the project idea to the endorsement/approval request
Project idea – Countries – NPFE (optional)
Project Concept – Agencies – PIF & PPG (templates)
GEFSEC PIF & PPG review, work program inclusion and Council approval
Project Preparation – Agencies
Project document – Agencies – FSP or MSP (EA) (templates)
GEFSEC review, CEO endorsement/approval and Council information

## Slide 5: Features of the GEF-5 project cycle
PIF submitted on a rolling basis;
18 months preparation for FSP: begins from date of Council approval of the work program till CEO endorsement of the final project document;
12 months preparation for MSP: applies only to those MSPs that requested PPG; begins from date of PIF approval by CEO to approval of final project document by CEO;
Program Framework Document (PFD) for Programmatic Approaches (PA) can be submitted only for Council meetings, scheduled twice a year (May and November)

## Slide 6: GEF Project Cycle Steps (1)
Main steps for Full-sized Projects (FSP):
Council/Secretariat:
Council approval of the work program, consisting of PIFs cleared by the CEO;
CEO endorsement of the final project document.
GEF Agency:
Approval of the project by the GEF Agency and implementation start;
Completion of implementation, terminal evaluation and financial closure.

## Slide 7: GEF Project Cycle Steps (2)
Main steps For Medium-sized Projects (MSP):
Single-step approval:
CEO approval of final MSP document;
Agency’s own internal approval and implementation starts.
Two-step step approval:
If PPG requested, submit PIF for CEO approval;
CEO approval of final project document;
Agency’s own internal approval and implementation starts.

## Slide 8
Medium-Sized Projects
* Agency approves MSP after CEO approval of the project and starts implementation.

## Slide 9: GEF Project Cycle Steps (3)
For Enabling Activities (two paths):
Direct Access (follow direct access policy):
Country submits EA proposal for CEO approval;
CEO and country sign Grant Agreement and implementation starts.
Follow existing procedures of applying EA grant through Agencies:
Agency submits EA proposal for CEO approval;
Agency follows its own internal approval procedure and implementation starts.

## Slide 10
Expedited Enabling Activity
Grant Agreement signed between Government and GEF CEO**
National Agency completes implementation of EA and submits Report to Convention
GEF Agency completes implementation of EA and country submits Reports to Convention
GEF Agency approves EA following CEO approval***
GEF Agency submits proposal for CEO approval
National Agency submits EA proposal to GEF Agency
* GEF Secretariat will follow the World Bank procedures in approving the proposal with final target
of sending a Grant Agreement to the recipient country and to be signed between CEO and the country.
National Agency submits EA proposal for CEO approval*

## Slide 11: Review Criteria for FSP/MSP
Country eligibility and ownership
Global Environment Benefits
GEF Focal area strategy
Agency’s Comparative advantage
Resource availability
Project consistency
Project design
Project financing and co-financing (baseline)
Monitoring and evaluation; and
Agency’s responses to comments and reviews.

## Slide 12: Country Endorsement (by Country National Operational Focal Point)
All PIFs should have OFP endorsement when submitting to GEF for clearance (in case of FSPs) or approval (in case of MSPs requesting a PPG)
Projects in biodiversity, climate change, and land degradation focal areas follow STAR rules

## Slide 13: Agency Fee
For stand-alone projects, a 10% fee based on the GEF amount for the project (project grant + PPG);
Agency fees for Programmatic Approaches vary depending on the type of Agency submitting the PA:
  Agencies with Board approving projects: 8%
  Agencies without Board approving projects: 9%
In case of project cancellation, all unused fees or a specific percentage should be returned to GEF Trust Fund.*
* Reference to Council paper, “Proposal for Revising the Fee System” (GEF/C.23/8/Rev.1) for fee return guidelines.

## Slide 14: Programmatic Approaches
Two Types of programmatic approaches, depending on the type of GEF Agency submitting the program:
Agencies with Board approving projects - those GEF Agencies meeting the criteria for delegated approval authority;
Agencies without Board approving projects - those GEF Agencies not meeting the criteria, such programs can be submitted by a Program Coordination Agency (PCA).

## Slide 15
Agency approves individual PIFs under the program
CEO endorses final project
documents
Agency approves final project according to Agency internal rule
Agency starts project implementation through completion
Council endorses Program Framework Document (PFD) through WP submission and approves PIFs submitted with PFD
Council approves Program Framework Document (PFD) through WP Submission
Council approves subsequent set of PIFs under the PFD submitted through WP
CEO endorses final project documents
Agency approves final project according to Agency internal rule
Agency starts project implementation through completion

## Slide 16: Role of STAP - Stand-alone Projects
STAP provides strategic scientific and technical advice to the GEF on the following:
FSPs:
Selectively screens PIFs received from Agencies when submitted to GEF Secretariat;
Screens all PIFs cleared by CEO for work program inclusion; screening reports are posted on the GEF website together with PIFs in the work program.
MSPs:
selectively screens MSP PIFs.

## Slide 17: Role of STAP
Programmatic Approaches (similar to FSPs):
Selectively screens PFDs received from Agencies when submitted to GEF Secretariat;
Screens all PFDs cleared by CEO for work program inclusion;
Screening reports are posted on the GEF website together with PFDs in the work program.

## Slide 18
THANK YOU FOR YOUR ATTENTION!
GEF website:
www.thegef.org