## Slide 1: GEF Project Cycle
Seminar for new GEF Project Agencies (Introduction to the GEF)
Washington, DC
May 28-29, 2015

## Slide 2: Types of GEF Projects
There are four types of GEF projects:
Full-Sized Projects (FSPs): GEF grant > $2 million
Medium-Sized Projects (MSPs): GEF grant < $2 million
Enabling Activities (EAs): GEF grant is capped by respective focal area threshold:
  Biodiversity and Climate Change = up to $500,000;
  Land Degradation = up to $150,000
  Chemical and Waste (MIA = $200,000; Persistent Organic Pollutants and ASGM NAP=$500,000)
Programmatic Approach (PA)
MIA=Minamata Convention Initial Assessment
ASGM NAP = “Artisanal and Small Scale Gold Mining” National Action Plan

## Slide 3: Project Cycle Steps
The GEF project cycle includes two major approval steps applicable for Full-Sized Projects:
Council and the GEF Secretariat:
  Council approval of work program
    work program consists of PIFs cleared by CEO
  CEO endorsement of the project document
    well-prepared projects document + CEO endorsement Request
GEF Agency:
  Approval of the project by the GEF Agency and implementation start;
  Completion of implementation, terminal evaluation and financial closure.

## Slide 4: Full-Sized Project Cycle
Council approval of Work Program*
CEO endorsement of project
GEF Agency approval of project**
Project implementation and continues to completion***
* Work Program consists of PIFs cleared by the CEO
** GEF Agency approval of project signifies start of project implementation
*** Project completion follows terminal evaluation and financial closure

## Slide 5: Medium-Sized Project Cycle
MSPs follow a simplified one-step approach as part of the project streamlining measures*:
Agencies and countries can prepare an MSP and submit it to the Secretariat for CEO approval once it is ready, on a rolling basis.
Follow the same GEF Agency internal approval process before implementation start.
MSP approval request template will build in a PPG request feature of up to $50,000 to help deflate the preparation expenses by the country on a reimbursement basis.
If needed, MSPs can also follow a two-step approach by submitting a PIF and PPG, if required. Such an approach will give the Agency/country a preparation timeline of 12 months for submitting the final MSP document for CEO approval before Agency approval and implementation start.

## Slide 6: Enabling Activities Project Cycle
Enabling Activities can follow two paths:
  Direct Access (follow direct access policy – applying the WB Operations Policies and Procedures):
    Country submits EA proposal for CEO approval;
    CEO and country sign Grant Agreement and implementation starts.
  Regular procedures of applying EA grant through Agencies:
    Agency submits EA proposal for CEO approval;
    Agency follows its own internal approval procedure and signing of a grant agreement with country before start of implementation.

## Slide 7: Programmatic Approach Cycle
A new programmatic approach processing modality was approved by Council in October 2014 Council meeting. This modality is being adopted for GEF-6 programmatic approaches (PA). This new modality is applicable for all GEF Partner Agencies.
The new PA modality includes two broad steps:
  Council approval of a Program Framework Document (PFD) included in a work program;
  CEO endorsement of fully prepared child projects under the program

## Slide 8: Features of a Program
The key document for a programmatic approach to be approved by Council is the submission of a Program Framework Document (PFD).
Features of a Program:
  Every programmatic approach will be managed by a Lead Agency;
  Lead Agency, in consultation with country and GEF Secretariat prepares a PFD including all the important elements for the program:
    Clear and measurable criteria for the selection of child projects
    A list of anticipated child projects,
    operational focal point endorsements for expected use of STAR allocations in the program, and
    A Program Commitment Deadline by which all child projects have to be submitted for CEO endorsement
  A child project can apply for project preparation funding through submission of a PPG Request.

## Slide 9: Agency Fees
Since January 2013, a new fee structure approved by Council in the June 2012 meeting has been implemented:
  For all types of projects: FSPs, MSPs, EAs and Programmatic Approaches:
    9.5 percent: GEF project grants are up to, and including, $10 million,
    9.0 percent: GEF Project grants above $10 million
  4.0 percent: Small Grants;
  9.0 percent: For new GEF Project Agencies accredited under the Pilot Program on Accrediting GEF Project Agencies, irrespective of project grant amount; GEF Project Agencies will not be compensated for any involvement in GEF “corporate activities” in which they may choose to become involved;
  The fees for PPGs follow the same rate of the related project.
  Tranche payment of Agency fees for FSPs: 40% are paid (meaning, committed by Trustee) when Council approves the work program and 60% by CEO endorsement.

## Slide 10: Project Review Criteria
Country eligibility and ownership
Global Environment Benefits
GEF Focal area strategy
Agency’s Comparative advantage
Resource availability
Project consistency
Project design
Project financing and co-financing
Monitoring and evaluation; and
Agency’s responses to comments and reviews.

## Slide 11: Country Endorsement
Endorsement by a national Operational Focal Point (OFP) is a requirement for all projects requesting GEF grant, and include the following:
  All PIFs entering the work program,
  Project Preparation Grants (PPGs),
  Request for CEO approval of MSP final projects (using the one-step approach),
  All EAs requesting CEO approval, and
  All regional projects where countries are identified require OFP endorsement from all countries for the amount from their country STAR allocations.
The only type of projects that do not require OFP endorsement letter are global projects where no specific country can be identified.

## Slide 12: GEF Project Cancellation Policy…..(1)
The GEF Project Cancellation Policy was updated and approved by Council in October 2015 and additional provisions were added to this update in the Council paper submitted for the June 2015 Council meeting.
The updated policy introduced the phased approach to implement the cancellation of projects as follows:
After 12 months of PIF approval by Council, a notification will be sent automatically from GEFSEC to the Agency, OFP of the recipient country to alert the remaining 6 months for submission of a FSP project for CEO endorsement.
After 18 months, the project will be cancelled and a notification will be sent by the Secretariat to all relevant stakeholders on the cancellation of the project.
The Secretariat will consider exception to the above cancellation only on extraordinary events, and if agreed, will notify Council.
Cancelled projects maybe resubmitted within a year for consideration for CEO endorsement, only if resources are available.

## Slide 13: GEF Project Cancellation Policy…..(2)
Cancellation of MSPs (that used the two-step approach) follows the same procedure as the FSPs except the timeline for MSP is 12 months.
Cancellation of child projects and uncommitted program amount:
  All child projects under a Program have to be submitted for CEO endorsement before the PFD Commitment Deadline and Trustee will commit funding for each child project upon CEO endorsement.
  Six months before the PFD commitment deadline, if there are still program funds awaiting submission of child projects for CEO endorsement, the Secretariat sends a notification to the Lead Agency notifying it of the upcoming cancellation of such program funds.
  After the passing of the agreed PFD commitment deadline, the CEO notifies the relevant Lead Agency and the Trustee of the cancellation for the remaining program funds.

## Slide 14: Council Papers on Project Cycle
Please consult the GEF website: www.thegef.org for all relevant project cycle papers for more detailed policies and procedures. To name a few:
GEF/C.31/7/Corr.1 GEF Project Cycle (Corrigendum) English
GEF/C.38/05/Rev.1 Streamlining the Project Cycle and
Refining the Programmatic Approach English
GEF/C.39/Inf.03 GEF Project and Programmatic Approach Cycles English
GEF/C.43/06 Streamlining of Project Cycle English
GEF/C.47/07 Improving the GEF Project Cycle English

## Slide 15: .
Thank you for your attention!
Questions?
Lily Uy Hale (Lhale@thegef.org)
Sr. Operations Officer
Operations and Business Strategy
GEF Secretariat
17